## ProjectMonitoring
Programme | Batch | 2021 - 2025 | Project: | Analyzing Social Media Posts for Mental Health Disorder Detection
| Group | 29 | Names: | Soumyadeep Nandy, Prithwish Sarkar, Sagnik Mukhopadhyay, Arkapratim Ghosh
Attendance (Insert below names)
Date | Project discussions |  |  |  | Semester | Deliverable | Issues | Guide's remark | Soumyadeep Nandy | Prithwish Sarkar | Sagnik Mukhopadhyay | Arkapratim Ghosh
2024-07-03 | Topic Discussion |  |  |  | 7 |  |  |  | Present | Present | Present | Present
2024-07-17 | Additions to Project Rough Diagram 1 |  |  |  | 7 |  | Classifying whether text is positve or negative | Using CNN | Present | Present | Present | Present
2024-07-29 | Finalizing Project Rough Diagram 2 |  |  |  | 7 |  | Data extraction from social media | Web Scraping and sample code | Present | Present | Present | Present
2024-08-24 | Synopsis Discussion |  |  |  | 7 |  |  |  | Present | Present | Present | Present
2024-09-09 | Dataset and it's content |  |  |  | 7 |  | Extensive Dataset Required (Reddit + Twitter) | Using Reddit API and Kaggle datasets | Present | Present | Present | Present
2024-09-28 | Mid-term Deliverables |  |  |  | 7 |  | What to include in the project report | Using Latex all sections should be filled and analysis results till date should be inserted | Present | Present | Present | Present
Total | [8 empty] | 100% | 100% | 100% | 100%
Overall | [8 empty] | 100% | 100% | 100% | 100%
Guide's signature:
(When maintained on hard-copy)

## Questions
Area | Question | Raised By | Status (Open / Closed) | Response | Response By
Topic Discussion | What classification model should be used for text? | Team | Closed | Using various algorithms like Naive Bayes, Random forest for a comparative study | Project Mentor
Additions to Rough Diagram 1 | What features should we extract from text data? | Team | Closed | Plan to use sentiment, keywords, and emotions. Bag Of Words Model will be helpful | Project Mentor
Rough Diagram 2 Finalization | What tools will be used for web scraping? | Team | Closed | Using Reddit API and sample web scraping code | Project Mentor
Synopsis Discussion | How detailed should the project synopsis be? | Team | Closed | Synopsis should include a short project overview | Project Mentor
Mid-term Deliverables | What format should the report follow? | Team | Closed | Use LaTeX and include all analysis and results | Project Mentor